## Action Plan
WHAT (PROJECT) | WHO (OWNER) | WHEN Expected completion date (MM/DD/YYYY) | IMPACT | ACTIONS MADE | NEXT ACTIONS
Inventory Position Report on PBI | J. Sanchez | 12.13.2019 | Large Cap Sites | 10.22.2019 Meeting with T. Corsaro to agreed on data. 11.01.2019 Pushing T. Corsaro to deliver query. 11.11.2019 Meeting with T. Corsaro for pushing. | 1. Obtain a query from IT. 2. Develop draft on PBI. 3. Meeting with H. Palomino to present draft - Improvements. 4. Testing data with sites.
Future PPV for SAP-WA sites | J. Sanchez | 11.15.2019 | Small Capital | 10.29.2019 Meeting with T. Corsaro matching old model data. 11.07.2019 Meeting with T. Corsaro testing data. | 1. Develop model on PBI. 2. Discuss data results with T. Corsaro and J. Leone. 3. Testing data with Small Cap leaders.
Saalfeld PPV automation on PBI | J. Sanchez | 01.10.2020 | SAP- Trumpf sites | 10.30.2019 Meeting with E. Thefaine and M. Hoffman review existing SAP query. 11.01.2019 Meeting with SAP expert trying to make a connection to ERP. | 1. Connect to SAP experts to pass Power BI error. 2. Create query/tables on SAP database. 3. ...
Price Increase Approval Workflow | J. Sanchez | 01.17.2020 | Large Cap Sites | 10.31.2019 Call with Santiago´s team to negotiate quotation. 11.07.2019 Have quotation ready and ask for H. Palomino approval to place PO. | 1.Send quotation received for approval. 2. Set up a meeting with Santiago´s team to start working on it.